Mekelle University

Office of the Vice-President for Research and Community Services

Monitoring and Evaluation Guideline

September, 2016

Mekelle University Monitoring and Evaluation Guideline on Research, Community Service and KTT Projects

Rational and Justification

Governments consider Universities as key institutions to train future leaders and conduct research and technological development. The case in Ethiopia is not an exception to this. Ethiopia considers human capital development as a central pillar of its development strategy. Moreover, it recognizes the role of higher education institutions as producers of knowledge, given the importance of knowledge as a source of development in present and future societies. This necessitated a dramatic increase in the number of higher education institutions and intake capacities.

This will then accelerate the economic and social development process of the nation. However, there is a growing concern about the weak link between research and development expenditure, and improvements in the living conditions of the people. This resonates with the findings of the study by DfID (2010). This is partly caused due to weak monitoring and evaluation (M&E) system on research, community service, and technology transfer projects.

We all assume university research to generate societal benefits in terms of expanding the frontiers of knowledge and contributing to the socio-economic development of nations. Its desired accomplishment indeed demands an effective monitoring and evaluation system that can track the project results and communicate them to various stakeholders (academic community, policy makers and industry players).

Furthermore, tracking the project process through monitoring facilitates feedback to relevant stakeholders to take timely and corrective measures that can ensure that the implementation of various projects is on track and capable of delivering the desired benefits. An effective M&E system also ensures accountability to project funders and general public thus promoting goodwill and continuous support and investments in research and related activities.

Therefore, the ability of universities to demonstrate how their research work, community service and technology transfer efforts benefits society through an effective M&E and communication system will stimulate public interest in funding research and its interlinked aspects and make them relevant to the development challenges of the nation. This guideline, hence, seeks to enhance the ability of Mekelle University to effectively track research process and outcomes and disseminating such information to relevant stakeholders to ensure accountability and linking research to national development efforts.

More specifically, it is aimed to track the process and outcomes and disseminate such findings in a manner appropriate to the various stakeholders

What is Monitoring and Evaluation?

- Monitoring: It is the systematic collection and analyses of data/information about the progress of a piece of work to provide feedback to relevant stakeholders to take timely and corrective measures to ensure that the intended project is on track towards achieving its objectives. It consists of operational and administrative activities that track resource acquisition and allocation, cost, production of goods and services, delivery of goods/services, and intermediate outcomes. Monitoring is continuous in its nature.

- Evaluation: It is the systematic collection and analysis of information on a project to ascertain the project performance and merit as well as draw lessons to guide the way forward. It is the process of determining the merit, worth or value of a project in terms of issues like relevance, cost- effectiveness and benefits to various stakeholders. Evaluation is periodic in nature. Evaluation exercises often seek to collect & analyze data on the following:

- Relevance (clarity  and appropriateness of project objectives, are the activities the best way of achieving the desired objectives)

- Effectiveness (the extent to which the objectives been achieved or the progress being made towards achieving the project objectives)

- Efficiency (how well activities are being carried out or is the project effort worth the investment)

- Outcome and impact  or results (tangible changes the projects bring over the life of the beneficiaries)

Accordingly, presented below is a M& E system that MU can introduce to ensure the efficiency and effectiveness of the various projects implemented under the name of research, community services and KTT.

- Undertake project monitoring works at an individual or institutional level

Monitoring projects may be done at individual and institutional levels. See the details below.

- Project monitoring at an individual project owner level: The individual project owner needs to monitor various dimensions of the project, including:

- Inputs: It indicates monitoring the resources applied in carrying out the project, such as staff, finance, and materials to ensure that these inputs are available at the right time in the right quantity and quality.

- The process of implementation: It is concerned with monitoring the activities and how they are implemented, as well as identifying barriers for effective project implementation.

- The outputs or project results: It is intended to ascertain the findings or end product of the project work.

- The impact of the project findings (results): Monitoring the uptake of the project findings (results) by various stakeholders and the impact it is having as well as identifying any uptake challenges that could be addressed by further project intervention.

- Institutional project monitoring: If project funding is attracted by a department/school/college/institute or individual project owner under the banner of the University, then the ultimate responsibility for the effective utilization of the project funds for the necessary project and deliver the expected outputs may rest with the Director of the Research and Postgraduate Office or UICL.  However, the directors may delegate such responsibilities to other people like the Head of College/Institute Research, Community Service and Postgraduate. At the institutional or wider University level, the areas worth monitoring include the following:

- Compliance: Mekelle University has rules and regulations to guide the way resources are mobilized and deployed for project work. There is need to track and ensure that these rules are being complied with.

- Tracking budget and utilization of project funds: This is to ensure that the project activities are within the budget provisions.

- Tracking project process: The focus is to ensure that the project is carried out as planned and that the intended milestones are attained along the way. This may require review of progress reports on projects and occasional field verification.

- Dissemination of outputs or results: The University should track and facilitate the process of sharing the project results or findings to various stakeholders.

- Conduct the required project evaluation works: The University can carry out the following evaluation types.

- Ex-ante evaluation: This is the one that takes place before the implementation of the intended project. It is usually called appraisal and is aimed at assessing the viability of the project.

- Formative evaluation: This is generally conducted during the implementation of the project, so as to identify any problems and take corrective measures. It seeks to fine-tune the project implementation.

- Summative evaluation: It is usually conducted at the end of the project so as to ascertain achievements or failures of the project.

- Ex-post evaluation: This is a type of project evaluation that takes place a few years after the expiration of the project to assess its impact or effects.

To be specific,

- All projects (research, community service and KTT) should pass through public defenses. This would help us to screen demand driven projects from those which emanate from the sole interest of the individual staff.

- It could be better if all university funded project owners use college/institute/ university cars in executing their projects. This will help us to ensure the appropriate collection of data and provision of desired services as per the proposal.

- A university organ (college dean/institute director, RCSPGO head, and department/school head) or an invited guest from the beneficiary office shall give an opening or closing speech while community service and KTT related affairs are organized by project owners. This will build the image of the university through mutual university-industry-community linkages. Moreover, it enables the concerned bodies to get (see) the intended results on the ground.

- Community service and KTT projects shall be backed up by evidence portraying the list of beneficiaries, time duration, address and role (position) of the trainees in their respective office. Moreover, the project owners should submit a detailed report indicting the gender based number of beneficiaries.  Each beneficiary (trainee) should also sign in an independent sheet (to be given by the office). This will help the RCSPGO to ensure that the project is implemented as per the objectives stated in the proposal as the head can communicate the reported beneficiaries being in office. This will be helpful in case the office can’t monitor the project execution on time.

- When staffs have projects on community service and KTT, they need to submit one training module to the RCSPGO in hard and soft copy using the language stated in the proposal. This would enable the office to compare the content and quality of the modules with respect to what is stated in the proposal. Moreover, it helps us to avoid duplication of the community service and/or KTT projects submitted on different times. Plagiarism can also be easily detected.

- The RCSPGO shall conduct periodic field visits to assess the status of the various projects funded and implemented by the university.

- RCSPGO has to be included in the clearance form. This will make the staff accountable as some staff members went for schooling without submitting a project report.

- The payment system for:

- Research projects shall be in 2 installments (50% for data collection & 50% for analysis). However, a technical progress report should be submitted and midterm report presentation is required to get the 2nd installment.

- Community service and KTT shall be in 2 installments (75% before training and 25% after training). However, a technical progress report should be submitted to get the 2nd installment.

- All research reports should then be reviewed by internal reviewers before they are presented at the research review day.

- The RCSPGO shall conduct project evaluation once all project owners submit their terminal reports. This would help the university to assess the real changes brought on the beneficiaries..

- In case the team founds a gap between what is reported and what is on the ground, the project team shall reimburse the fund and be responsible for the upcoming punishment accordingly.