## Slide 1
Basic Project
Management Process
Larry Creel
July 11, 2003
Notes: <number>
Adapted from Aftershock: Helping People Through Change by H. Woodward, S. Buchholz, K. Hess (Wiley 1987)

## Slide 2
What is a Project?
Definition 1
A temporary endeavor undertaken to create a unique product, service or result. (Project Management Institute)
Definition 2
A series of interrelated activities undertaken to accomplish a specific goal or end result. (Kepner-Tregoe)
Project
References: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 2000 Edition Project Management Institute;
Project Management, 1987 Kepner-Tregoe, Inc.
Notes: <number>

## Slide 3
What is Project Management?
Definition 1
The application of knowledge, skills, tools and techniques to project activities to meet the project requirements. (Project Management Institute)
Definition 2
The actions taken to define the project’s requirements; plan the activities to accomplish the requirements; and ensure successful project implementation. (Kepner-Tregoe)
Project Management
References: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 2000 Edition Project Management Institute;
Project Management, 1987 Kepner-Tregoe, Inc.
Notes: <number>

## Slide 4
What is a Project Life Cycle?
A collection of generally sequential project phases whose name and number are determined by the control needs of the organization or organizations involved in the project. (Project Management Institute)
Project Life Cycle
Reference: A Guide to the Project Management Body of Knowledge (PMBOK Guide) 2000 Edition Project Management Institute
Notes: <number>

## Slide 5
Typical Project Life Cycle
Adapted from Project Management: A Managerial Approach by J.R. Meredith & S.J. Mantel Jr. (5th Ed., Wiley 2003)
Idea / concept developed
Project authorized
Plans developed / executed
Progress monitored / controlled
Results delivered
Final report issued
Definition & Planning
Selection & Authorization
Monitor & Control
Close Out
Conception
Launch Plan
Beginning
Stage
Middle
Stage
End
Stage
Time

## Slide 6
Example – Progress Through the Life Cycle
Adapted from Project Management: A Managerial Approach by J.R. Meredith & S.J. Mantel Jr. (5th Ed., Wiley 2003)
Construction projects tend to follow this pattern.
% Project Completion
Time
Slow finish
Slow start
Quick momentum
0
100
Beginning
Middle
End

## Slide 7
Overview
Basic project management definitions
Life cycle of a project
Basic project management process
We will discuss
Notes: <number>

## Slide 8
Basic Project Management Process
Launch Plan
Project Completed
Project Authorized
Define Project
Develop Detailed Plan
Monitor & Control Progress
Close Out Project
Feedback
Adapted from Project Management, 1987 Kepner-Tregoe, Inc. and Effective Project Management by R.K. Wysocki, R. Beck Jr. & D.B. Crane (Wiley, 1995)

## Slide 9
State need, problem or opportunity.
Define project objectives.
Identify success criteria.
List assumptions, risks and obstacles.
Define project scope (what will be delivered).
Define Project
Adapted from Project Management, 1987 Kepner-Tregoe, Inc. and Effective Project Management by R.K. Wysocki, R. Beck Jr. & D.B. Crane (Wiley, 1995)
Project Completed
Project Authorized
Define Project
Feedback
Develop Plan
Launch Plan
Monitor & Control
Close Out Project

## Slide 10
Identify project activities.
Estimate activity duration.
Determine resource requirements.
Construct and analyze project network.
Prepare project schedule.
Develop Detailed Plan
Adapted from Project Management, 1987 Kepner-Tregoe, Inc. and Effective Project Management by R.K. Wysocki, R. Beck Jr. & D.B. Crane (Wiley, 1995)
Project Completed
Project Authorized
Define Project
Feedback
Develop Plan
Launch Plan
Monitor & Control
Close Out Project

## Slide 11
Recruit and organize project team.
Establish team operating rules.
Level project resources.
Assign work.
Launch Plan
Adapted from Project Management, 1987 Kepner-Tregoe, Inc. and Effective Project Management by R.K. Wysocki, R. Beck Jr. & D.B. Crane (Wiley, 1995)
Project Completed
Project Authorized
Define Project
Feedback
Develop Plan
Launch Plan
Monitor & Control
Close Out Project

## Slide 12
Establish progress reporting system.
Set up change control process.
Define problem escalation process.
Monitor progress vs. plan.
Revise project plan as required.
Monitor & Control Progress
Adapted from Project Management, 1987 Kepner-Tregoe, Inc. and Effective Project Management by R.K. Wysocki, R. Beck Jr. & D.B. Crane (Wiley, 1995)
Project Completed
Project Authorized
Define Project
Feedback
Develop Plan
Launch Plan
Monitor & Control
Close Out Project

## Slide 13
Obtain customer acceptance.
Install project deliverables.
Complete project documentation.
Complete post-implementation audit.
Issue final project report.
Close Out Project
Adapted from Project Management, 1987 Kepner-Tregoe, Inc. and Effective Project Management by R.K. Wysocki, R. Beck Jr. & D.B. Crane (Wiley, 1995)
Project Completed
Project Authorized
Define Project
Feedback
Develop Plan
Launch Plan
Monitor & Control
Close Out Project

## Slide 14
PM Process Summary
Launch Plan
Recruit and organize project team
Establish team operating rules
Level project resources
Assign work
Monitor & Control Progress
Establish progress reporting system
Set up change control process
Define problem escalation process
Monitor progress vs. plan
Revise project plan
Close Out Project
Obtain client acceptance
Install project deliverables
Complete project documentation
Complete post-implementation audit
Issue final project report
Develop Detailed Plan
Identify project activities
Estimate activity duration
Determine resource requirements
Construct / analyze project network
Prepare project schedule
Define Project
State need, problem or opportunity
Define project objectives
Identify success criteria
List assumptions, risks and obstacles
Define project scope
Feedback
Adapted from Project Management, 1987 Kepner-Tregoe, Inc. and Effective Project Management by R.K. Wysocki, R. Beck Jr. & D.B. Crane (Wiley, 1995)
Notes: <number>

## Slide 15
Summary
A project is a temporary endeavor undertaken to create a unique product, service or result.
A project has a life cycle that consists of stages
  Beginning stage (idea / approval)
  Middle stage (work intensive)
  End stage (final result)
To be successful projects must be defined, planned, controlled and closed out using a well defined project management process.
Notes: <number>

## Slide 16
References
A Guide to the Project Management Body of Knowledge (Project Management Institute, 2000)
Effective Project Management by R.K. Wysocki, R. Beck Jr., & D.B. Crane (Wiley, 1995)
Project Management (Kepner-Tregoe, Inc., 1987)
Project Management: A Managerial Approach by J.R. Meredith & S.J. Mantel Jr. (5th Ed., Wiley 2003)
Notes: <number>

## Slide 17
?
Notes: <number>

## Slide 18
Larry Creel, PMP
MKPO Consulting
2413 S. Kentucky
Sedalia, MO 65301
660.826.8392
Contact Information
Notes: <number>