## Slide 1: Today’s Lesson
PROJECT PLANNING

## Slide 2: Lesson Learning Outcomes
At the conclusion of this lesson, the student should be able to:
  Justify the need for planning in achieving project success.
  Understand the planning process
  Apply basic planning tools for project management.

## Slide 3: WHY PLAN ?
PROJECT PEOPLE needs:
    To know exactly what their ROLE is
    What are EXPECTED &
    WHEN is it WANTED.
  CUSTOMERS WANTS:
    To be confident that Contractor knows what they are DOING, &
    Have CLEAR IDEA of where they are going.
  MANAGEMENT & his PROJECT MANAGER NEEDS:
    To know whether the project is:
      ON SCHEDULE & WITIN BUDGET, &
      Whether CORRECTIVE ACTIONS are needed.

## Slide 4
Reduces the
Impact of Change
Provides
Direction
Minimizes Waste
and Redundancy
Sets Standards to
Facilitate
Control
Reasons
for Planning
Notes: <number>
5
Planning can be either formal or informal, depending on the time frame and amount of documentation. Because of the dynamic and unpredictable business environment, it is important that managers plan and plan well. There are four reasons for planning.
First, planning coordinates effort by giving direction to managers and non-managers.
Second, planning reduces uncertainty by forcing managers to look ahead, anticipate change, and develop appropriate responses.
Third, planning reduces redundancy.By coordinating efforts, wasteful and inefficient activities can be prevented.
Fourth, planning establishes standards or objectives that facilitate control over the process of achieving goals.

## Slide 5: OBJECTIVES OF PLANNING
Provide a STRUCTURED BASIS for work execution
Derive PROCEDURES TO CONTROL work effectively
Obtain OPTIMUM RESULTS – TIME & COST
Establish a STANDARD of PERFORMANCE
Reduce RISKS & UNCERTAINTIES to a minimum
Ensure CLEAR UNDERSTANDING of project objectives.

## Slide 6: MAIN COMPONENT OF PLANNING
TO ESTABLISH THE DESIRED OBJECTIVES
DETERMINE STRATEGY TO ACHIEVE RESULTS
DERIVE PLAN & SCHEDULE SHOWING WHEN RESULTS CAN BE ACHIEVE
PROJECTIONS OF WHAT WILL HAPPEN AT CERTAIN SPECIFIC POINT
DERIVE A BUDGET TO ESTABLISH EXPENDITURE
ESTABLISH PROCEDURES FOR CONTROL & COMMUNICATION
SET STANDARD OF PERFORMANCE MEASUREMENT

## Slide 7: PLANNING START
The STARTING POINT for a project is a proper understanding of the requirements –
  What exactly is the project suppose to achieve?
  The NEXT STEP is to establish the FUNDAMENTAL BUILDING BLOCK of the project planning.

## Slide 8: Project Charter
What must be done?
  What are the required resources?
  What are the constraints?
  What are the short and long term implications?
Why do it?
When must it be done?
Where must it be done?
Who does what?
  Who is behind the project?
  Who is funding the project?
  Who is performing the work of the project?
Notes: <number>

## Slide 9: Project Charter
Who
What
Where
Why
When
Notes: <number>

## Slide 10: Project Charter
Project Goal & Objective
Sponsor
Stakeholders
Timeline
Resources required
Deliverables
Decision making
Assumptions
Risks
Business process changes
Project manager
Project team
Budget
Signatures
Notes: <number>
Examples for Handouts
What is the RISK of NOT doing the project?
Your target audience for the charter is the LAY EXECUTUVE. If you can write it such that there is no ambiguity there, you are most of the way there.

## Slide 11
Project Planning Core Processes
Scope Planning
Activity
Definition
Scope
Definition
Resource
Planning
Cost
Estimating
Activity
Duration
Estimates
Activity
Sequencing
Develop
Network
Diagram
Cost
Budgeting
Project Plan
Risk Mgmt.
Planning
Define
Logic
Contingency
Reserves
Resource
leveling

## Slide 12: Planning Facilitating Processes
Quality
Planning
Risk
Identification
Communication
Planning
Risk
Quantification
Risk
Response
Development
Organizational
Planning
Staff
Acquisition
Procurement
Planning
Solicitation
Planning

## Slide 13: PROJECT PLANNING PROCESS
TOOLS
&
TECHNIQUES

## Slide 14
Work Breakdown Structure ( WBS )

## Slide 15: To answer the following questions
"How many tasks should this project have?"
"How much detail should I have in the project schedule?"

## Slide 16: What is WBS?
WBS is a map of a project
A Work Breakdown Structure is a results-oriented family tree that captures all the work of a project in an organized way.
graphically as a hierarchical tree
categories and tasks or the indented task list that appears in your Gantt chart schedule
Work of project is subdivided into smaller work elements
Lowest level of WBS is called work package

## Slide 17: History of the WBS
The WBS was initially developed by the U.S. defense
described in Military Standard (MIL-STD) 881B (25 Mar 93) as follows:
  "A work breakdown structure is a product-oriented family tree composed of hardware, software, services, data and facilities .... [it] displays and defines the product(s) to be developed and/or produced and relates the elements of work to be accomplished to each other and to the end product(s)."

## Slide 18
The Work Breakdown Structure (WBS) is used to provide the framework for organizing and managing the work.
break the project into pieces, organize the pieces in a logical way using a WBS, and then get help from the rest of your project team

## Slide 19: WBS - Objectives
To divide the project into hierarchical units of tasks, work packages & work units
Reduce risk of missing something & logically identify all work activities
Split project into tangible deliverable items

## Slide 24: Hierarchical Breakdown of the WBS
4-3

## Slide 25: Work Package
Short duration
Have start and stop point, No. of resources and Cost
Each work package must be independent of other packages.

## Slide 26: Why use WBS?
Help PM to identify all work elemments
To integrate the project with current organisation
To establish a basis for control

## Slide 27: How WBS is done?
Identify the major project work deliverables first
Then define the sub deliverables that are necessary to accomplish the major deliverables
Repeat this process until the sub deliverables is small enough to be managed by one person
Top management deals major work
Supervisors deal with smaller sub deliverables

## Slide 28: Benefit of WBS
Make it possible to plan,schedule and budget
Gives frameworkfor tracking cost and performance
Defines communication channels
Assist in understanding and coordinating many parts of project
Problems can be quickly solved because structure integrate work and responsibility

## Slide 29: Work Breakdown Structure
4-4

## Slide 30: Integration of WBS and OBS
4-5

## Slide 31: Breakdown
By function
  C&S
  M&E
  Landscape
By product
  Runaway
  Terminal
  Hotel
  Rower

## Slide 32
Depends on the easier way
Sometimes combination of both
Do Not breakdown to too detail
Activities of the project are the one at the bottom

## Slide 33: Breakdown ends
….when this questions answered
  Can you visualise?
  Can you estimate the time to construct?
  Can you estimate the resources accurately?

## Slide 34: SAMPLE WORK BREAKDOWN STRUCTURE
Build a Garage
Wall & Floor
Finish
External
Works
Roof
R.C. Structure
Framework
Foundation
Excavation
Ground
Floor
Footing
Stump
Beam
&
Slab
Column
Roof Cover
Brickwork
Waterproof
Plaster
RWDP
Screed
&
Paint
Drains
Roads
Streetlight

## Slide 35: Sequence the Work Activities
1. Excavation
4. Ground
Floor
2. Footing
3. Stump
6. Beam
&
Slab
5. Column
7. Roof Cover
10. Brickwork
8. Waterproof
11. Plaster
9. RWDP
12. Screed & Paint
13. Drains
14. Roads
15. Streetlight

## Slide 36: Estimate Duration & Identify Resources Required
1. Excavation – 1 day
4. Ground
Floor – 2 days
2. Footing – 1 day
3. Stump – 1 day
6. Beam
&
Slab – 3 days
5. Column – 2 days
7. Roof Cover - 4 days
10. Brickwork – 5 days
8. Waterproof – 3 days
11. Plaster - 3 days
9. RWDP – 1 day
12. Screed & Paint – 6 days
13. Drains – 2 days
14. Roads – 7 days
15. Streetlight – 1 day
Carpenter 3 manday
Barbender 2 manday
Concretor 2 manday

## Slide 37: Estimate Cost & Develop Budget
1. Excavation – 1 day
4. Ground
Floor – 2 days
2. Footing – 1 day
3. Stump – 1 day
6. Beam
&
Slab – 3 days
5. Column – 2 days
7. Roof Cover - 4 days
10. Brickwork – 5 days
8. Waterproof – 3 days
11. Plaster - 3 days
9. RWDP – 1 day
12. Screed & Paint – 6 days
13. Drains – 2 days
14. Roads – 7 days
15. Streetlight – 1 day
Labor Cost
Carpenter 3 manday @ $50pd = $150
Barbender 2 manday @ $40pd = $80
Concretor 2 manday @ $30pd = $60
Material Cost
Formwork 10ms @ $30/ms = $300
Steel Bars 0.1mt @2000/mt = $200
Concrete 10mc @$200/mc = $2000
Plant & machinery
Excavator 1 day @ $300 = $300
Tool Rental (lump sum) = $100
Total Cost = $3190
Project Budget
Total cost (all activities)
+
Prelim & Mobilization cost
+
overhead
+
risk contingency

## Slide 38: Set the Milestone
EVERY PROJECT HAS MILESTONE:
START DATE
FINISH DATE
USING THE WBS, YOU CAN DECIDE THE KEY STAGES AND ASSIGN THEIR COMPLETION MILESTONE STATUS.
Project Scheduling

## Slide 39: MILESTONE CHART
Contract Award |  |  |  |  |  |  | 
Foundation Works |  |  |  |  |  |  | 
RC Frame |  |  |  |  |  |  | 
Roof Cover |  |  |  |  |  |  | 
Wall & Floor Finishes |  |  |  |  |  |  | 
External Works |  |  |  |  |  |  | 
EVENT | JAN | FEB. | MAR. | APRIL | MAY | JUNE | JULY
PLANNED
ACTUAL
Current
Reporting Period

## Slide 40: PROJECT SCHEDULING
Project schedule establishes the time parameters of the project;
Determines:
  What needs to be done,
  Who will do it, &
  What duration will it take.

## Slide 41: STEPS REQUIRED TO DEVELOP THE SCHEDULE:
Define Project Objectives
Sequence Work Activities
Estimate Time
&
Resources
Develop WBS
Reconcile Schedule
with Resources
Review Schedule
with Time Constraint
Determine Dependencies
(Logic)
Get Management &
Customer’s approval

## Slide 42: Scheduling Techniques
Bar Charting
Network Analysis
  Pert Chart
  CPM
  GERT
  PDM

## Slide 43: Scheduling Technique: BAR CHARTING
Most common & widely used.
Used for relative simple project.
For short term & weekly programming.
For communication purpose.
Provide graphic medium on which milestones can be entered.

## Slide 44: Scheduling technique: Network Analysis
Network shows a project as a system of activities
Tools & Techniques
PERT CHART
CPM
PDM

## Slide 45: ARROW DIAGRAMS (Activity –on-Arrow Network)
1
2
remove
engine
overhaul
engine
replace
engine
3
4

## Slide 46: ACTIVITY-ON-NODE NETWORK
REMOVE
ENGINE
(6 HRS.)
OVERHAUL
ENGINE
(72 HRS.)
REPLACE
ENGINE
(12 HRS.)

## Slide 47: TIME ANALYSIS OF A NETWORK
Forward Pass
A Forward Pass is perform to find the earliest event time (Activity-on-Arrow network), or the earliest start and finish time of activities (PDM Network)
Backward Pass
A Backward Pass is performed to find the latest event time or latest finish and start time.

## Slide 48: CRITICAL PATH
The longest sequential path of activities through the network which connects the beginning and the end of the project
A (2 days)
B (3 days)
E (5 days)
C (5 days)
F (6 days)
D (3 days)
START
FINISH

## Slide 49: Use of Dependencies (Logic)
Finish Start
Activity 1
Activity 2
Start Start
(SS)
Activity 3
Activity 4
Finish Finish
(FF)
Activity 6
Activity 5

## Slide 50: Project Planning & Scheduling Software
Microsoft Project 98
Artemis Project
Primavera P3
Suretrack
Project Scheduler
Harvard Project Manager
Visual Planner
MacProject II
Cosmos
OpenPlan
Quick Schedule Plus
Primavera
Ms Project